## Sheet1
Who | What | When to finish
Vineet | PM2.5 change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | NO2 change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | PM10 change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | CO change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | o3 change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | so2 change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet | aqi change for Melbourne before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | PM2.5 change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | NO2 change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | PM10 change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | CO change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | o3 change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | so2 change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Alison | aqi change for Perth before and during covid 19 (2019 - 2020H1) | Tue 7/7/20
Vineet, Alison, Tracey | Put everything together | Wed 8/7/2020
Vineet, Alison, Tracey | Put everything together | Thu 8/7/2020
Alison | Making slides | Fri 9/7/2020